## Work Distribution
TASKS | SUB-TASKS | DESCRIPTION | ESTIMATED TIME TO COMPLETE | TEAM MEMBER RESPONSIBLE
Pre-processing | Data Identification | Identify the type of data that we wish to use for this project and research to verify if large volume of data is available. | 5 days | Vishvak
| Subset Identification | Identify a smaller sub set of chosen data which would be used to pupulate the Database created | 1 day | Vishvak
| Database Creation | Create a database which would be populated with data from previous steps | 1 day | Ragini
| Query Identification | Identify the type of query that is common on the data and finalise it for execution | 60 min | Vivek
| Performance Metrics | Identify the various query performance metrics used widely in the industry | 2 days | Vivek
| Document Query Results | Run the query from above step and document performance stats | 30 minutes | Ragini
Indexing | Building an index | Create an index.The index stores the value of a specific field or set of fields, ordered by the value of the field | 1 day | Vivek
| Synchronizing an index | Indexing will attempt to re-index any items that have previously failed to be indexed | 30 minutes | Vivek
| Verifying an index | Different checks will then be performed depending on the Verification level | 30 minutes | Ragini
| Upgrading an index | Once the upgrade has completed successfully, the old index volume will be replaced with the new volume, | 1 day | Vishvak
| Rebuilding an index | Rebuild index volumes .Once the rebuild has completed successfully, the old index volume will be replaced with the new volume. | 1 day | Ragini
Sharding | Creating a Directory for Config Server | The first step to be performed in order to set up MongoDB Sharding would be to create a separate directory for Config Server. | 40 minutes | Vishvak
| Starting MongoDB Instance in Configuration Mode | One Server has to be set up as the Configuration Server. | 30 minutes | Vivek
| Starting Mongos Instance | Once the Configuration Server has been set up, the Mongos Instance can be started | 30 minutes | Ragini
| Connecting to Mongos Instance | A connection can be formed to the Mongos Instance | 30 minutes | Vivek
| Adding Servers to Clusters | All Servers that have to be included in the Cluster have to be added | 30 minutes | Vishvak
| Enabling Sharding for Database | Once the Sharded Cluster has been set up, Sharding for the required database has to be enabled. | 40 minutes | Ragini.
Validation | Database size | Increase the size of the database and check for results, time taken to run queries on indexed datasets versus time taken to run queries on non-indexed datasets. | 1 day | Team

## Risk Analysis
Risks | Impact | Severity | Risk Management Measure
Data collection from a reliable source, correctness of data, which includes security issues. | As this is the building block of the project, if data chosen is not correct correct it might led to project failure directly. | High | Evalutaion of data carefully before insertion into database, try to work on smaller datasets initially. Check if the source is reliable, if data is being taken from an open source.
Scope creep/Change in scope due to misinterpretation of requirements. | If realized in initial phases can be corrected but if realized at later changes can led to project failure. | High | Careful analysis of the type of data that is to be worked on. No sensitive data to be included, for example banking information.
Incompatibility of existing softwares | Team might not be in sync even if one resource doesn’t have the required software tools to work on | High | Choose software keeping in mind the system configuration of all team members.
Performance issues | Queries might take longer time to run or system crash. | Medium | Work on smaller datasets initially and gradually increase them ensuring there is no rapid increase of load on the system.
Lack of functional knowledge | We might not be able implement our action plan and delay in project deadlines. | Low | Time taken into consideration to learn and then implement.
Human error/incompetence | Delay in project submissions, time utilized in finding errors. | Low | Re-check work and manual testing required.
Schedule Changes | Schedule changes will lead to confusions and delays in the action plan and we might get off track. | Medium | Keep a buffer amount in the planning of project to fit in time for any delays (if any)